## Testing
MBV4 QC Database
File name: MBV4_Test_QC_Data_2nd_Batch_proto.xlsx
F. Tang, January 18 -- November 5, 2021
Test run-1: Board #1-2
Board# | POWER | Volatge (V) | Current (mA) | Total Current (mA) | After FPGA loaded (mA) | Pass/Fail | Date | Note | Burn-in Status | Burn-in Table # | Burn-in Date | Burn-in Note | Full Test Status | Full Test Date | Full test Note
1 | [5 empty] | Pass |  | Damaged at CERN, received on July 26, 2021, found 8 inputs components of ADC9 were ripped off. | Skip |  | N/A | run up schedule for demenstrator | Pass | N/A
2 | [5 empty] | Pass |  |  | Skip |  | N/A | run up schedule for demenstrator | Pass | N/A
Test run-2: Board #3-10
Board# | POWER | Volatge (V) | Current (mA) | Total Current (mA) | After FPGA loaded (mA) | Pass/Fail |  | Note | Burn-in Status |  | Burn-in Date | Burn-in Note | Full Test Status | Full Test Date | Full test Note
3 | [5 empty] | Pass |  | data is not inputed yet | Done |  | 2021-08-23 |  | Pass | 2021-08-23
Board# | POWER | Volatge (V) | Current (mA) | Total Current (mA) | After FPGA loaded (mA) | Pass/Fail |  | Note | Burn-in Status |  | Burn-in Date | Burn-in Note | Full Test Status | Full Test Date | Full test Note
4 | P10VB | 9.55 |  | 267 |  | Pass |  |  | Skip |  | N/A | run up schedule for demenstrator | Pass | N/A
4 | P5V0B | 4.98 |  |  |  | Pass
4 | N5V0B | 0.212 (-5.09) |  |  |  | Fail |  | Pass after replacing U2, LT3759
4 | P2V5B | 2.526 |  |  |  | Pass
4 | P1V8B | 1.791 |  |  |  | Pass
4 | P1V2B | 1.179 |  |  |  | Pass
4 | P10VA | 9.54 |  |  |  | Pass
4 | P5V0A | 4.99 |  |  |  | Pass
4 | N5V0A | -5.06 |  |  |  | Pass
4 | P2V5A | 2.524 |  |  |  | Pass
4 | P1V8A | 1.788 |  |  |  | Pass
4 | P1V2A | 1.179 |  |  |  | Pass
Board# | POWER | Volatge (V) | Current (mA) | Total Current (mA) | After FPGA loaded (mA) | Pass/Fail |  | Note | Burn-in Status |  | Burn-in Date | Burn-in Note | Full Test Status | Full Test Date | Full test Note
5 | P10VB | 9.56 |  | 277 |  | Pass |  | Damaged at CERN, received in early June 2021 for repaires. Found 2 components ripped off and A-side 1.8V shorted to GROUND, thermal image show all ADC chips on A-side with "hot spot". | Skip |  | N/A | run up schedule for demenstrator | Pass | N/A
5 | P5V0B | 4.98 |  |  |  | Pass
5 | N5V0B | -5.06 |  |  |  | Pass
5 | P2V5B | 2.52 |  |  |  | Pass
5 | P1V8B | 1.792 |  |  |  | Pass
5 | P1V2B | 1.176 |  |  |  | Pass
5 | P10VA | 9.57 |  |  |  | Pass
5 | P5V0A | 4.99 |  |  |  | Pass
5 | N5V0A | -5.09 |  |  |  | Pass
5 | P2V5A | 2.513 |  |  |  | Pass
5 | P1V8A | 1.79 |  |  |  | Pass
5 | P1V2A | 1.177 |  |  |  | Pass
Board# | POWER | Volatge (V) | Current (mA) | Total Current (mA) | After FPGA loaded (mA) | Pass/Fail |  | Note | Burn-in Status |  | Burn-in Date | Burn-in Note | Full Test Status | Full Test Date | Full test Note
6 | P10VB | 9.57 |  | 257 |  | Pass |  |  | Skip |  |  | run up schedule for demenstrator | Pass | N/A
6 | P5V0B | 5 |  |  |  | Pass
6 | N5V0B | -5.1 |  |  |  | Pass
6 | P2V5B | 2.52 |  |  |  | Pass
6 | P1V8B | 1.793 |  |  |  | Pass
6 | P1V2B | 1.18 |  |  |  | Pass
6 | P10VA | 9.57 |  |  |  | Pass
6 | P5V0A | 4.97 |  |  |  | Pass
6 | N5V0A | -5.08 |  |  |  | Pass
6 | P2V5A | 2.5213 |  |  |  | Pass
6 | P1V8A | 1.78 |  |  |  | Pass
6 | P1V2A | 1.177 |  |  |  | Pass
Board# | POWER | Volatge (V) | Current (mA) | Total Current (mA) | After FPGA loaded (mA) | Pass/Fail |  | Note | Burn-in Status |  | Burn-in Date | Burn-in Note | Full Test Status | Full Test Date | Full test Note
7 | P10VB | 9.47 |  | 271 |  | Pass |  |  | Skip |  |  | run up schedule for demenstrator | Pass | N/A
7 | P5V0B | 4.98 |  |  |  | Pass
7 | N5V0B | -5.05 |  |  |  | Pass |  | Issue found at CERN on March 29, 2021. N5VB failed, found U2-pin8 was bad soldering, possibllly shocking of shipment, 3/31/2021
7 | P2V5B | 2.53 |  |  |  | Pass
7 | P1V8B | 1.784 |  |  |  | Pass
7 | P1V2B | 1.179 |  |  |  | Pass
7 | P10VA | 9.47 |  |  |  | Pass
7 | P5V0A | 4.97 |  |  |  | Pass
7 | N5V0A | -5.08 |  |  |  | Pass
7 | P2V5A | 2.525 |  |  |  | Pass
7 | P1V8A | 1.78 |  |  |  | Pass
7 | P1V2A | 1.18 |  |  |  | Pass
Board# | POWER | Volatge (V) | Current (mA) | Total Current (mA) | After FPGA loaded (mA) | Pass/Fail |  | Note | Burn-in Status |  | Burn-in Date | Burn-in Note | Full Test Status | Full Test Date | Full test Note
8 | P10VB | 9.58 |  | 270 |  | Pass |  |  | Skip |  |  | run up schedule for demenstrator | Pass | N/A
8 | P5V0B | 4.96 |  |  |  | Pass
8 | N5V0B | -5.08 |  |  |  | Pass
8 | P2V5B | 2.527 |  |  |  | Pass
8 | P1V8B | 1.787 |  |  |  | Pass
8 | P1V2B | 1.178 |  |  |  | Pass
8 | P10VA | 9.57 |  |  |  | Pass
8 | P5V0A | 4.96 |  |  |  | Pass
8 | N5V0A | -5.08 |  |  |  | Pass
8 | P2V5A | 2.528 |  |  |  | Pass
8 | P1V8A | 1.789 |  |  |  | Pass
8 | P1V2A | 1.178 |  |  |  | Pass
Board# | POWER | Volatge (V) | Current (mA) | Total Current (mA) | After FPGA loaded (mA) | Pass/Fail |  | Note | Burn-in Status |  | Burn-in Date | Burn-in Note | Full Test Status | Full Test Date | Full test Note | Full Test Date
9 | P10VB | 9.56 |  | 270 |  | Pass |  |  | Skip |  |  | run up schedule for demenstrator | Pass | N/A
9 | P5V0B | 4.97 |  |  |  | Pass
9 | N5V0B | 2.26 (-5.08) |  |  |  | Fail |  | (1) Pass after replacing U2, LT3759 (2) Failed again at CERN on March 28, 2021, touched U2-pin8 with solder, back to work on March 31, 2021
9 | P2V5B | 2.518 |  |  |  | Pass
9 | P1V8B | 1.79 |  |  |  | Pass
9 | P1V2B | 1.178 |  |  |  | Pass
9 | P10VA | 9.55 |  |  |  | Pass
9 | P5V0A | 4.98 |  |  |  | Pass
9 | N5V0A | -5.07 |  |  |  | Pass
9 | P2V5A | 2.524 |  |  |  | Pass
9 | P1V8A | 1.787 |  |  |  | Pass
9 | P1V2A | 1.177 |  |  |  | Pass
Board# | POWER | Volatge (V) | Current (mA) | Total Current (mA) | After FPGA loaded (mA) | Pass/Fail |  | Note | Burn-in Status |  | Burn-in Date | Burn-in Note | Full Test Status | Full Test Date | Full test Note
10 | P10VB | 9.56 |  | 258 |  | Pass |  |  | Skip |  |  | run up schedule for demenstrator | Pass | N/A
10 | P5V0B | 4.99 |  |  |  | Pass
10 | N5V0B | 2.222 (-5.05) |  |  |  | Fail |  | Pass after replacing U2, LT3759
10 | P2V5B | 2.519 |  |  |  | Pass
10 | P1V8B | 1.788 |  |  |  | Pass
10 | P1V2B | 1.178 |  |  |  | Pass
10 | P10VA | 9.56 |  |  |  | Pass
10 | P5V0A | 4.97 |  |  |  | Pass
10 | N5V0A | -5.08 |  |  |  | Pass
10 | P2V5A | 2.516 |  |  |  | Pass
10 | P1V8A | 1.786 |  |  |  | Pass
10 | P1V2A | 1.176 |  |  |  | Pass
Board# | POWER | Volatge (V) | Current (mA) | Total Current (mA) | After FPGA loaded (mA) | Pass/Fail |  | Initial Note | Burn-in Status |  | Burn-in Date | Burn-in Note | Full Test Status | Full Test Date | Full test Note
11 | All local votages Passed tests |  |  | 269 |  | Pass | 2021-07-19 |  | Skip |  |  | run up schedule for demenstrator | Pass | 2021-07-27
12 | All local votages Passed tests |  |  | 269 |  | Pass | 2021-07-19 |  | Skip |  |  | run up schedule for demenstrator | Pass | 2021-07-26
13 | All local votages Passed tests |  |  | 269 |  | Pass | 2021-08-02 |  | Skip |  |  | run up schedule for demenstrator | Pass | 2021-08-04
14 | All local votages Passed tests |  |  | 265 |  | Pass | 2021-08-02 |  | Skip |  |  | run up schedule for demenstrator | Pass | 2021-08-04
15 | All local votages Passed tests |  |  | 262 |  | Pass | 2021-08-02 |  | Skip |  |  | run up schedule for demenstrator | Pass | 2021-08-04
16 | All local votages Passed tests |  |  | 258 |  | Pass | 2021-08-02 |  | Skip |  |  | run up schedule for demenstrator | Pass | 2021-08-04
17 | All local votages Passed tests |  |  | 262 |  | Pass | 2021-08-02 |  | Skip |  |  | run up schedule for demenstrator | Pass | 2021-08-04
18 | All local votages Passed tests |  |  | 264 |  | Pass | 2021-08-02 |  | Skip |  |  | run up schedule for demenstrator | Pass | 2021-08-05
19 | All local votages Passed tests |  |  | 269 |  | Pass | 2021-08-02 | ACC. RM 124, good card for using in comparasion in repairing for other cards | Skip |  |  | run up schedule for demenstrator | Pass | 2021-08-04
20 | All local votages Passed tests |  |  | 264 |  | Pass | 2021-08-02 |  | Done |  | 2021-08-11 | All burn-in @65C for 120 Hours | Pass | 2021-08-04
21 | All local votages Passed tests |  |  | 260 |  | Pass | 2021-08-02 |  | Done |  | 2021-08-11 |  | Pass | 2021-08-04
22 | All local votages Passed tests |  |  | 260 |  | Pass | 2021-08-02 |  | Done |  | 2021-08-11 |  | Pass | 2021-08-04
23 | All local votages Passed tests |  |  | 258 |  | Pass | 2021-08-02 |  | Done |  | 2021-08-11 |  | Pass | 2021-08-05
24 | All local votages Passed tests |  |  | 262 |  | Pass | 2021-08-02 |  | Done |  | 2021-08-11 |  | Pass | 2021-08-05
25 | All local votages Passed tests |  |  | 257 |  | Pass | 2021-08-02 |  | Done |  | 2021-08-11 |  | Pass | 2021-08-16
26 | All local votages Passed tests |  |  | 264 |  | Pass | 2021-08-02 |  | Done |  | 2021-08-11 |  | Pass | 2021-08-16
27 | All local votages Passed tests |  |  | 261 |  | Pass | 2021-08-02 |  | Done |  | 2021-08-11 |  | Pass | 2021-08-17
28 | All local votages Passed tests |  |  | 260 |  | Pass | 2021-08-09 |  | Done |  | 2021-08-23 |  | Pass | 2021-08-23
29 | All local votages Passed tests |  |  | 257 |  | Pass | 2021-08-09 |  | Done |  | 2021-08-11 |  | Pass | 2021-08-17
30 | All local votages Passed tests |  |  | 262 |  | Pass | 2021-08-09 |  | Done |  | 2021-08-11 |  | Pass | 2021-08-17
31 | All local votages Passed tests |  |  | 258 |  | Pass | 2021-08-09 |  | Done |  | 2021-08-11 |  | Pass | 2021-08-17
32 | All local votages Passed tests |  |  | 255 |  | Pass | 2021-08-09 |  | Done |  | 2021-08-11 |  | Pass | 2021-08-18
33 | All local votages Passed tests |  |  | 264 |  | Pass | 2021-08-09 |  | Done |  | 2021-08-11 |  | Pass | 2021-08-17
34 | All local votages Passed tests |  |  | 265 |  | Pass | 2021-08-09 | Int. 5 did not work, output contantly flat at "1"s . 8/17/21, ACC. RM 124. Found I2C clk and data traces over etched and broken, it was intially repaired by the PCB house, and repaired by jumping wires at the Shop and works. Sent back to Kelby 8/18/21 | Done |  | 2021-08-11 |  | Pass | 2021-08-18 | See. Intial note
35 | All local votages Passed tests |  |  | 265 |  | Pass | 2021-08-09 |  | Done |  | 2021-08-11 |  | Pass | 2021-08-17
36 | All local votages Passed tests |  |  | 267 |  | Pass | 2021-08-09 |  | Done |  | 2021-08-11 |  | Pass | 2021-08-17
37 | All local votages Passed tests |  |  | 257 | 469 | Pass | 2021-08-16 | Terasic cable works, all-volt cable only good on A1, B1 | Done |  | 2021-08-23 |  | Pass | 2021-08-23
38 | All local votages Passed tests |  |  | 254 | 470 | Pass | 2021-08-16 | Terasic cable works, all-volt cable only good on A1, B1 | Done |  | 2021-08-23 |  | Pass | 2021-08-23
39 | All local votages Passed tests |  |  | 259 | 467 | Pass | 2021-08-16 | Terasic cable works, all-volt cable only good on A1, B1 | Done |  | 2021-08-23 |  | Pass | 2021-08-23
40 | All local votages Passed tests |  |  | 256 | 468 | Pass | 2021-08-16 | Terasic cable works, all-volt cable only good on A1, B1 | Done |  | 2021-08-23 |  | Pass | 2021-08-23
41 | All local votages Passed tests |  |  | 255 | 471 | Pass | 2021-08-16 | Terasic cable works, all-volt cable only good on A1, B1 | Done |  | 2021-08-23 |  | Pass | 2021-08-23
42 | All local votages Passed tests |  |  | 261 | 470 | Pass | 2021-08-16 | Terasic cable works, all-volt cable only good on A1, B1 | Done |  | 2021-08-23 |  | Pass | 2021-08-23
43 | All local votages Passed tests |  |  | 257 | 467 | Pass | 2021-08-16 | Terasic cable works, all-volt cable only good on A1, B1 | Done |  | 2021-08-23 |  | Pass | 2021-08-23
44 | All local votages Passed tests |  |  | 259 | 469 | Pass | 2021-08-16 | Terasic cable works, all-volt cable only good on A1, B1 | Done |  | 2021-08-23 |  | Pass | 2021-08-23
45 | All local votages Passed tests |  |  | 255 | 466 | Pass | 2021-08-16 | Terasic cable works, all-volt cable only good on A1, B1 | Done |  | 2021-08-23 |  | Pass | 2021-08-23
46 | All local votages Passed tests |  |  | 256 | 467 | Pass | 2021-08-16 | Terasic cable works, all-volt cable only good on A1, B1 | Done |  | 2021-08-23 |  | Pass | 2021-08-23
47 | All local votages Passed tests |  |  | 257 | 469 | Pass | 2021-08-23 | Terasic cable | Done | T1 | 2021-08-30 |  | Pass | 2021-08-30
48 | All local votages Passed tests |  |  | 260 | 471 | Pass | 2021-08-23 | Terasic cable | Done | T1 | 2021-08-30 |  | Pass | 2021-08-30
49 | All local votages Passed tests |  |  | 256 | 466 | Pass | 2021-08-23 | Terasic cable | Done | T1 | 2021-08-30 |  | Pass | 2021-08-30
50 | All local votages Passed tests |  |  | 263 | 473 | Pass | 2021-08-23 | Terasic cable | Done | T1 | 2021-08-30 |  | Pass | 2021-08-30
51 | All local votages Passed tests |  |  | 262 | 473 | Pass | 2021-08-23 | Terasic cable | Done | T2 | 2021-08-30 |  | Pass | 2021-08-31
52 | All local votages Passed tests |  |  | 259 | 470 | Pass | 2021-08-23 | Terasic cable | Done | T2 | 2021-08-30 |  | Pass | 2021-08-31
53 | All local votages Passed tests |  |  | 257 | 467 | Pass | 2021-08-23 | Terasic cable | Done | T2 | 2021-08-30 |  | Pass | 2021-08-31
54 | All local votages Passed tests |  |  | 259 | 470 | Pass | 2021-08-23 | Terasic cable | Done | T2 | 2021-08-30 |  | Pass | 2021-08-31
55 | All local votages Passed tests |  |  | 260 | 470 | Pass | 2021-08-23 | Terasic cable | Done | T3 | 2021-08-30 |  | Pass | 2021-08-31
56 | All local votages Passed tests |  |  | 261 | 472 | Pass | 2021-08-23 | Terasic cable | Done | T3 | 2021-08-30 |  | Pass | 2021-08-31
57 | All local votages Passed tests |  |  | 262 | 473 | Pass | 2021-08-23 | Terasic cable | Done | T3 | 2021-08-30 |  | Pass | 2021-08-31
58 | All local votages Passed tests |  |  | 261 | 472 | Pass | 2021-08-23 | Terasic cable | Done | T3 | 2021-08-30 |  | Pass | 2021-08-31
59 | All local votages Passed tests |  |  | 267 | 478 | Pass | 2021-09-07 | Terasic cable | Done | T3 | 2021-09-14 |  | Pass | 2021-09-14
60 | All local votages Passed tests |  |  | 258 | 471 | Pass | 2021-09-11 | Terasic cable | Done |  | 2021-09-20 |  | Pass | 2021-09-22
61 | All local votages Passed tests |  |  | 258 | 469 | Pass | 2021-09-27 | Terasic cable | Done |  | 2021-10-02 |  | Pass | 2021-10-05
62 | All local votages Passed tests |  |  | 264 | 475 | Pass | 2021-09-27 | Terasic cable | Done |  | 2021-10-02 |  | Pass | 2021-10-05
63 | All local votages Passed tests |  |  | 254 | 466 | Pass | 2021-09-27 | Terasic cable | Done |  | 2021-10-02 | ADC3 low gain data failed reported by Kelby | Fail | 2021-10-05 | ADC3 LG bias network RH2 open at one end, bad solder repaired, it works | 2021-11-01
64 | All local votages Passed tests |  |  | 252 | 465 | Pass | 2021-09-27 | Not passed DC volatge tests in Bestproto, Found F1 was borken in Eshop, after fixed F1, it works | Done |  | 2021-10-02 |  | Pass | 2021-10-05
65 | All local votages Passed tests |  |  | 255 | 466 | Pass | 2021-09-07 | Copper balanced PCB | Done |  | 2021-09-14 |  | Pass | 2021-09-14
66 | All local votages Passed tests |  |  | 256 | 467 | Pass | 2021-09-07 | Copper balanced PCB | Done |  | 2021-09-14 |  | Pass | 2021-09-14
67 | All local votages Passed tests |  |  | 266 | 477 | Pass | 2021-09-07 | Copper balanced PCB | Done |  | 2021-09-14 |  | Pass | 2021-09-14
68 | All local votages Passed tests |  |  | 255 | 466 | Pass | 2021-09-07 | Copper balanced PCB | Done |  | 2021-09-14 |  | Pass | 2021-09-14
69 | All local votages Passed tests |  |  | 260 | 470 | Pass | 2021-09-07 | Copper balanced PCB | Done |  | 2021-09-14 |  | Pass | 2021-09-14
70 | All local votages Passed tests |  |  | 268 | 475 | Pass | 2021-09-07 | Copper balanced PCB | Done |  | 2021-09-14 |  | Pass | 2021-09-14
71 | All local votages Passed tests |  |  | 262 | 475 | Pass | 2021-09-07 | Copper balanced PCB | Done |  | 2021-09-14 |  | Pass | 2021-09-14
72 | All local votages Passed tests |  |  | 257 | 474 | Pass | 2021-09-07 | Copper balanced PCB | Done |  | 2021-09-14 |  | Pass | 2021-09-14
73 | All local votages Passed tests |  |  | 258 | 469 | Pass | 2021-09-07 | Copper balanced PCB | Done |  | 2021-09-14 |  | Pass | 2021-09-14
74 | All local votages Passed tests |  |  | 261 | 470 | Pass | 2021-09-11 | Copper balanced PCB | Done |  | 2021-09-20 |  | Pass | 2021-09-22
75 | All local votages Passed tests |  |  | 256 | 468 | Pass | 2021-09-11 | Copper balanced PCB | Done |  | 2021-09-20 |  | Pass | 2021-09-22
76 | All local votages Passed tests |  |  | 271 | 481 | Pass | 2021-09-11 | Copper balanced PCB | Done |  | 2021-09-20 |  | Pass | 2021-09-22
77 | All local votages Passed tests |  |  | 262 | 470 | Pass | 2021-09-11 | Copper balanced PCB | Done |  | 2021-09-20 |  | Pass | 2021-09-22
78 | All local votages Passed tests |  |  | 264 | 474 | Pass | 2021-09-11 | Copper balanced PCB | Done |  | 2021-09-20 |  | Pass | 2021-09-22
79 | All local votages Passed tests |  |  | 263 | 472 | Pass | 2021-09-11 | Copper balanced PCB | Done |  | 2021-09-20 |  | Pass | 2021-09-22
80 | All local votages Passed tests |  |  | 261 | 471 | Pass | 2021-09-11 | Copper balanced PCB | Done |  | 2021-09-20 | #80 had a problem with counting the frame clock from ADC3, pass tests out of burn-in, firmware corrupted during burn-in | Pass | 2021-09-22
81 | All local votages Passed tests |  |  | 258 | 472 | Pass | 2021-09-11 | Copper balanced PCB | Done |  | 2021-09-20 | #81 had a problem with counting the frame clocks from ADC1-ADC11, only ADC0 fram clock was ok, pass tests out of burn-in, firmware corrupted during burn-in | Pass | 2021-09-22
82 | All local votages Passed tests |  |  | 260 | 468 | Pass | 2021-09-11 | Copper balanced PCB | Done |  | 2021-09-20 |  | Pass | 2021-09-22
83 | All local votages Passed tests |  |  | 262 | 469 | Pass | 2021-09-20 | Copper balanced PCB | Done |  | 2021-09-27 |  | Pass | 2021-09-27
84 | All local votages Passed tests |  |  | 257 | 466 | Pass | 2021-09-20 | Copper balanced PCB | Done |  | 2021-09-27 |  | Pass | 2021-09-27
85 | All local votages Passed tests |  |  | 262 | 471 | Pass | 2021-09-20 | Copper balanced PCB | Done |  | 2021-09-27 |  | Pass | 2021-09-27
86 | All local votages Passed tests |  |  | 264 | 473 | Pass | 2021-09-20 | Copper balanced PCB | Done |  | 2021-09-27 |  | Pass | 2021-09-27
87 | All local votages Passed tests |  |  | 259 | 469 | Pass | 2021-09-20 | Copper balanced PCB | Done |  | 2021-09-27 |  | Pass | 2021-09-27
88 | All local votages Passed tests |  |  | 257 | 467 | Pass | 2021-09-20 | Copper balanced PCB | Done |  | 2021-09-27 |  | Pass | 2021-09-28
89 | All local votages Passed tests |  |  | 257 | 467 | Pass | 2021-09-20 | Copper balanced PCB | Done |  | 2021-09-27 |  | Pass | 2021-09-28
90 | All local votages Passed tests |  |  | 259 | 470 | Pass | 2021-09-20 | Copper balanced PCB | Done |  | 2021-09-27 |  | Pass | 2021-09-28
91 | All local votages Passed tests |  |  | 267 | 473 | Pass | 2021-09-20 | Copper balanced PCB | Done |  | 2021-09-27 |  | Pass | 2021-09-28
92 | All local votages Passed tests |  |  | 261 | 471 | Pass | 2021-09-20 | Copper balanced PCB | Done |  | 2021-10-02 |  | Pass | 2021-09-28
93 | All local votages Passed tests |  |  | 267 | 475 | Pass | 2021-09-27 | Copper balanced PCB | Done |  | 2021-10-02 |  | Pass | 2021-10-05
94 | All local votages Passed tests |  |  | 261 | 471 | Pass | 2021-09-27 | Copper balanced PCB | Done |  | 2021-10-02 | B-side N5V fails reported by Kelby | Fail | 2021-10-05 | It works without any repairs after recheck | 2021-11-01
95 | All local votages Passed tests |  |  | 257 | 465 | Pass | 2021-09-27 | Copper balanced PCB | Done |  | 2021-10-02 |  | Pass | 2021-10-05
96 | All local votages Passed tests |  |  | 260 | 469 | Pass | 2021-09-27 | Copper balanced PCB | Done |  | 2021-10-02 |  | Pass | 2021-10-05
97 | All local votages Passed tests |  |  | 258 | 467 | Pass | 2021-09-27 | Copper balanced PCB | Done |  | 2021-10-02 |  | Pass | 2021-10-05
98 | All local votages Passed tests |  |  | 260 | 468 | Pass | 2021-09-27 | Copper balanced PCB | Done |  | 2021-10-02 |  | Pass | 2021-10-05
99 | All local votages Passed tests |  |  | 263 | 473 | Pass | 2021-09-27 | Copper balanced PCB | Done |  | 2021-10-02 |  | Pass | 2021-10-05
100 | All local votages Passed tests |  |  | 257 | 466 | Pass | 2021-09-27 | Copper balanced PCB | Done |  | 2021-10-02 |  | Pass | 2021-10-05

## Shiping
BOX # | Qty | BOARDS# | BOARD1-SN | BOARD2-SN | BOARD3-SN | BOARD4-SN | BOARD5-SN | BOARD6-SN | Packed on | Current Location | Final Destinaton | Received Date | Note
0 | 5 | #00, #21, #22, #23, #34 | [6 empty] | 2021-08-24 | Shipping to Clermont-Ferrand | David Calvet | 2021-08-13 | #00 added
0A | 1 | #2 | [8 empty] | CERN, Irakli | 2021-08-26
0B | 1 | #5 | [8 empty] | Tang's home | 2021-11-04
0C | 2 | #1, #19 | [8 empty] | Tang's office | 2021-11-04
1 | 6 | #27, #29, #30, #31, #33, #36 | 20LLCHI10V40027 | 20LLCHI10V40030 | 20LLCHI10V40031 | 20LLCHI10V40029 | 20LLCHI10V40033 | 20LLCHI10V40036 | 2021-08-24 | MCP 019 | CERN, Irakli | 2021-11-18 | Packed
2 | 6 | #24, #25, #26, #35, #39, #46 | 20LLCHI10V40039 | 20LLCHI10V40046 | 20LLCHI10V40024 | 20LLCHI10V40025 | 20LLCHI10V40026 | 20LLCHI10V40035 | 2021-08-24 | MCP 019 | CERN, Irakli | 2021-11-18 | Packed
3 | 6 | #03, #20, #28, #37, #40, #44 | 20LLCHI10V40040 | 20LLCHI10V40003 | 20LLCHI10V40037 | 20LLCHI10V40028 | 20LLCHI10V40044 | 20LLCHI10V40020 | 2021-08-24 | MCP 019 | CERN, Irakli | 2021-11-18 | Packed
4 | 6 | #32, #38, #41, #42, #43, #45 | 20LLCHI10V40042 | 20LLCHI10V40032 | 20LLCHI10V40041 | 20LLCHI10V40038 | 20LLCHI10V40045 | 20LLCHI10V40043 | 2021-08-24 | MCP 019 | CERN, Irakli | 2021-11-18 | Packed
5 | 6 | #52, #53, #54, #55, #57, #58 | 20LLCHI10V40055 | 20LLCHI10V40053 | 20LLCHI10V40057 | 20LLCHI10V40058 | 20LLCHI10V40054 | 20LLCHI10V40052 | 2021-08-31 | MCP 019 | CERN, Irakli | 2021-11-18 | Packed
6 | 6 | #47, #48, #49, #50, #51, #56 | 20LLCHI10V40051 | 20LLCHI10V40047 | 20LLCHI10V40049 | 20LLCHI10V40048 | 20LLCHI10V40050 | 20LLCHI10V40056 | 2021-08-31 | MCP 019 | CERN, Irakli | 2021-11-18 | Packed
7 | 6 | #66, #67, #68, #69, #72, #73 | 20LLCHI10V40066 | 20LLCHI10V40067 | 20LLCHI10V40068 | 20LLCHI10V40069 | 20LLCHI10V40072 | 20LLCHI10V40073 | 2021-09-21 | MCP 019 | CERN, Irakli | 2021-11-18 | Packed
8 | 6 | #74, #75, #79, #80, #81, #82 | 20LLCHI10V40074 | 20LLCHI10V40075 | 20LLCHI10V40079 | 20LLCHI10V40080 | 20LLCHI10V40081 | 20LLCHI10V40082 | 2021-09-21 | MCP 019 | CERN, Irakli | 2021-11-18 | Packed
9 | 6 | #59, #71, #65, #70, #77, #78 | 20LLCHI10V40059 | 20LLCHI10V40071 | 20LLCHI10V40065 | 20LLCHI10V40070 | 20LLCHI10V40077 | 20LLCHI10V40078 | 2021-09-21 | MCP 019 | CERN, Irakli | 2021-11-18 | Packed
10 | 6 | #76, #88, #87, #86, #85, #84 | 20LLCHI10V40076 | 20LLCHI10V40088 | 20LLCHI10V40087 | 20LLCHI10V40086 | 20LLCHI10V40085 | 20LLCHI10V40084 | 2021-09-21 | MCP 019 |  |  | Packed
11 | 6 | #83, #60, #89, #62, #96, #90 | 20LLCHI10V40083 | 20LLCHI10V40060 | 20LLCHI10V40089 | 20LLCHI10V40062 | 20LLCHI10V40096 | 20LLCHI10V40090 | 2021-10-05 | MCP 019 |  |  | Packed
12 | 6 | #91, #92, #95, #93, #61, #64 | 20LLCHI10V40091 | 20LLCHI10V40092 | 20LLCHI10V40095 | 20LLCHI10V40093 | 20LLCHI10V40061 | 20LLCHI10V40064 | 2021-10-05 | MCP 019 |  |  | Packed
13 | 6 | #63, #94, #97, #98, #99, #100 | [6 empty] | 2021-11-04 | MCP 007 | Kelby |  | Not packed